## 1. Gantt Chart
SVV BALAJI - PROJECT GANTT CHART
Revised 19-Aug-2026. Week 1 commenced 04-Aug-2026. Amber bars are B2C activities added by Decision 1 and are conditional on written agreement of cost and timeline (action A-10). Red line marks the current reporting week. Start / Finish columns remain the agreed baseline (A-01) and are deliberately not moved when an activity finishes early - the bar shows the plan, the % Done column shows reality against it.
[7 empty] | 04-Aug | 11-Aug | 18-Aug | 25-Aug | 01-Sep | 08-Sep | 15-Sep | 22-Sep | 29-Sep | 06-Oct | 13-Oct | 20-Oct | 27-Oct | 03-Nov | 10-Nov | 17-Nov | 24-Nov | 01-Dec | 08-Dec | 15-Dec | 22-Dec
WBS | Activity | Owner | Start | Finish | % Done | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
WS1 | BACKEND API / PLATFORM
WS1.1 | Foundation: architecture, auth, roles & permissions, CI | Ujjawal | 1 | 1 | 100% | Complete | 04-Aug: 3
WS1.2 | Farm sourcing: farmer registry, traceability ID, agreements, seed, training, field monitoring | Ujjawal | 1 | 2 | 100% | Complete | 04-Aug: 3; 11-Aug: 3
WS1.3 | Procurement: planning, harvest inspection, collection, batching, warehouse & inventory | Ujjawal | 2 | 3 | 100% | Complete | 11-Aug: 3; 18-Aug: 3
WS1.4 | Processing: cleaning/grading, recipes, production, QA, packaging, finished goods | Ujjawal | 3 | 4 | 100% | Complete | 18-Aug: 3; 25-Aug: 3
WS1.5 | Sales & order fulfilment (B2B), dispatch & delivery - channel-aware order model | Ujjawal | 2 | 5 | 80% | In progress | bar: 11-Aug to 01-Sep
WS1.6 | Channel pricing engine: dated price lists per channel (B2B / B2C) [NEW - Decision 1] | Ujjawal | 2 | 3 | 100% | Complete | 11-Aug: 3; 18-Aug: 3
WS1.7 | Consumer (B2C) commerce APIs: accounts, cart, checkout, order tracking [NEW - Decision 1] | Ujjawal | 5 | 7 | 0% | Conditional | 01-Sep: 4; 08-Sep: 4; 15-Sep: 4
WS1.8 | Customer feedback, complaints & analytics | Ujjawal | 7 | 8 | 0% | Not started | bar: 15-Sep to 22-Sep
WS1.9 | Notifications, document management & reporting engine | Ujjawal | 8 | 9 | 0% | Not started | bar: 22-Sep to 29-Sep
WS2 | ADMIN WEB PANEL (FRONTEND)
WS2.1 | Panel scaffolding, auth, role-based navigation | Raunak | 2 | 4 | 100% | Complete | 11-Aug: 3; 18-Aug: 3; 25-Aug: 3
WS2.2 | Master data, farmer & channel pricing screens | Raunak | 4 | 6 | 100% | Complete | 25-Aug: 3; 01-Sep: 3; 08-Sep: 3
WS2.3 | Procurement, warehouse & inventory screens | Raunak | 6 | 8 | 100% | Complete | 08-Sep: 3; 15-Sep: 3; 22-Sep: 3
WS2.4 | Production, recipe & quality screens | Raunak | 8 | 10 | 100% | Complete | 22-Sep: 3; 29-Sep: 3; 06-Oct: 3
WS2.5 | Sales, dispatch & delivery screens (channel-aware) | Raunak | 10 | 12 | 100% | Complete | 06-Oct: 3; 13-Oct: 3; 20-Oct: 3
WS2.6 | Dashboards, reports & analytics screens | Raunak | 12 | 13 | 20% | In progress | bar: 20-Oct to 27-Oct
WS3 | MOBILE APPS & CONSUMER CHANNEL
WS3.1 | Agriculture Expert app (offline field visits, crop monitoring, training logs) | Raunak | 10 | 12 | 60% | In progress | bar: 06-Oct to 20-Oct
WS3.2 | Sales Executive app (B2B order capture) | Raunak | 12 | 14 | 0% | Not started | bar: 20-Oct to 03-Nov
WS3.3 | Warehouse app (stock, batch scanning) | Ujjawal | 13 | 14 | 0% | Not started | bar: 27-Oct to 03-Nov
WS3.4 | Delivery app (route, OTP, proof of delivery) | Ujjawal | 14 | 15 | 0% | Not started | bar: 03-Nov to 10-Nov
WS3.5 | Consumer app / website (B2C): browse, cart, accounts, tracking, QR scan [NEW - Decision 1] | Raunak | 13 | 17 | 0% | Conditional | 27-Oct: 4; 03-Nov: 4; 10-Nov: 4; 17-Nov: 4; 24-Nov: 4
WS4 | INTEGRATIONS & INFRASTRUCTURE
WS4.1 | Cloud object storage (photos, documents, video) | Ujjawal | 5 | 6 | 80% | In progress | bar: 01-Sep to 08-Sep
WS4.2 | WhatsApp Business API (via BSP) | Ujjawal | 9 | 10 | 0% | Not started | bar: 29-Sep to 06-Oct
WS4.3 | SMS / OTP gateway | Ujjawal | 9 | 10 | 0% | Not started | bar: 29-Sep to 06-Oct
WS4.4 | GST e-invoicing (IRN/IRP) & e-way bill via GST Suvidha Provider | Ujjawal | 7 | 9 | 0% | Not started | bar: 15-Sep to 29-Sep
WS4.5 | Payment gateway - Razorpay (B2C confirmed, was on hold) | Ujjawal | 12 | 13 | 0% | Conditional | 20-Oct: 4; 27-Oct: 4
WS5 | QUALITY, DEPLOYMENT & HANDOVER
WS5.1 | Automated test suite & continuous integration | Ujjawal | 1 | 16 | 45% | In progress | bar: 04-Aug to 17-Nov
WS5.2 | Staging environment & deployment pipeline | Ujjawal | 2 | 3 | 0% | Not started | bar: 11-Aug to 18-Aug
WS5.3 | Data migration (existing customer & product masters) | Raunak | 14 | 15 | 0% | Not started | bar: 03-Nov to 10-Nov
WS5.4 | User acceptance testing (UAT) with SVV Balaji - B2B | Joint | 15 | 17 | 0% | Not started | bar: 10-Nov to 24-Nov
WS5.5 | Backups, monitoring & disaster recovery | Ujjawal | 15 | 16 | 0% | Not started | bar: 10-Nov to 17-Nov
WS5.6 | Training & handover | Joint | 17 | 18 | 0% | Not started | bar: 24-Nov to 01-Dec
WS5.7 | Go-live & hypercare - B2B launch | Joint | 18 | 18 | 0% | Not started | bar: 01-Dec
WS5.8 | B2C UAT & consumer channel launch [NEW - Decision 1] | Joint | 19 | 21 | 0% | Conditional | 08-Dec: 4; 15-Dec: 4; 22-Dec: 4
LEGEND
Complete
In progress / planned
Blocked - awaiting client decision
B2C scope - conditional on A-10 (cost & timeline agreement)
Red vertical line = current reporting week (w/c 18-Aug-2026)
Bars are formula-driven: edit the Start / Finish week columns and the chart updates automatically.

## 2. Schedule Baseline
SVV BALAJI - REVISED ACTIVITY-WISE SCHEDULE BASELINE
Revised 11-Aug-2026. Decision 1 (both B2B and B2C sales channels with separate pricing) adds four activities beyond the signed scope of work: WS1.6, WS1.7, WS3.5 and WS5.8, plus activation of WS4.5.
Weeks are numbered from Week 1 commencing 04-Aug-2026. B2C activities extend the programme to Week 21 and are conditional on written agreement of cost and timeline (action A-10). The B2B launch remains at Week 18. Planned start / finish weeks are the agreed baseline and are not revised when an activity delivers early; % Complete carries the actual position. Progress updated 19-Aug-2026.
WBS | Workstream / Activity | FRD Ref | Owner | Planned Start (Wk) | Planned Finish (Wk) | Weight % | % Complete | Status
WS1 | BACKEND API / PLATFORM
WS1.1 | Foundation: architecture, auth, roles & permissions, CI | FRD 5,6 | Ujjawal | W1 | W1 | 3% | 100% | Complete
WS1.2 | Farm sourcing: farmer registry, traceability ID, agreements, seed, training, field monitoring | FRD 7-12 | Ujjawal | W1 | W2 | 5% | 100% | Complete
WS1.3 | Procurement: planning, harvest inspection, collection, batching, warehouse & inventory | FRD 13-17 | Ujjawal | W2 | W3 | 5% | 100% | Complete
WS1.4 | Processing: cleaning/grading, recipes, production, QA, packaging, finished goods | FRD 18-23 | Ujjawal | W3 | W4 | 6% | 100% | Complete
WS1.5 | Sales & order fulfilment (B2B), dispatch & delivery - channel-aware order model | FRD 24-28 | Ujjawal | W2 | W5 | 6% | 80% | In progress
WS1.6 | Channel pricing engine: dated price lists per channel (B2B / B2C) [NEW - Decision 1] | FRD 24-26 | Ujjawal | W2 | W3 | 2% | 100% | Complete
WS1.7 | Consumer (B2C) commerce APIs: accounts, cart, checkout, order tracking [NEW - Decision 1] | FRD 29-30 | Ujjawal | W5 | W7 | 4% | 0% | Conditional
WS1.8 | Customer feedback, complaints & analytics | FRD 31-34 | Ujjawal | W7 | W8 | 3% | 0% | Not started
WS1.9 | Notifications, document management & reporting engine | FRD 33-35 | Ujjawal | W8 | W9 | 2% | 0% | Not started
WS2 | ADMIN WEB PANEL (FRONTEND)
WS2.1 | Panel scaffolding, auth, role-based navigation | FRD 5 | Raunak | W2 | W4 | 3% | 100% | Complete
WS2.2 | Master data, farmer & channel pricing screens | FRD 6-12 | Raunak | W4 | W6 | 5% | 100% | Complete
WS2.3 | Procurement, warehouse & inventory screens | FRD 13-17 | Raunak | W6 | W8 | 4% | 100% | Complete
WS2.4 | Production, recipe & quality screens | FRD 18-23 | Raunak | W8 | W10 | 4% | 100% | Complete
WS2.5 | Sales, dispatch & delivery screens (channel-aware) | FRD 24-28 | Raunak | W10 | W12 | 3% | 100% | Complete
WS2.6 | Dashboards, reports & analytics screens | FRD 34 | Raunak | W12 | W13 | 3% | 20% | In progress
WS3 | MOBILE APPS & CONSUMER CHANNEL
WS3.1 | Agriculture Expert app (offline field visits, crop monitoring, training logs) | FRD 12 | Raunak | W10 | W12 | 5% | 60% | In progress
WS3.2 | Sales Executive app (B2B order capture) | FRD 24 | Raunak | W12 | W14 | 5% | 0% | Not started
WS3.3 | Warehouse app (stock, batch scanning) | FRD 16-17 | Ujjawal | W13 | W14 | 3% | 0% | Not started
WS3.4 | Delivery app (route, OTP, proof of delivery) | FRD 27-28 | Ujjawal | W14 | W15 | 4% | 0% | Not started
WS3.5 | Consumer app / website (B2C): browse, cart, accounts, tracking, QR scan [NEW - Decision 1] | FRD 29-32 | Raunak | W13 | W17 | 7% | 0% | Conditional
WS4 | INTEGRATIONS & INFRASTRUCTURE
WS4.1 | Cloud object storage (photos, documents, video) | FRD 35 | Ujjawal | W5 | W6 | 2% | 80% | In progress
WS4.2 | WhatsApp Business API (via BSP) | FRD 33 | Ujjawal | W9 | W10 | 1% | 0% | Not started
WS4.3 | SMS / OTP gateway | FRD 28,33 | Ujjawal | W9 | W10 | 1% | 0% | Not started
WS4.4 | GST e-invoicing (IRN/IRP) & e-way bill via GST Suvidha Provider | FRD 26 | Ujjawal | W7 | W9 | 2% | 0% | Not started
WS4.5 | Payment gateway - Razorpay (B2C confirmed, was on hold) | FRD 26 | Ujjawal | W12 | W13 | 1% | 0% | Conditional
WS5 | QUALITY, DEPLOYMENT & HANDOVER
WS5.1 | Automated test suite & continuous integration | - | Ujjawal | W1 | W16 | 2% | 45% | In progress
WS5.2 | Staging environment & deployment pipeline | - | Ujjawal | W2 | W3 | 1% | 0% | Not started
WS5.3 | Data migration (existing customer & product masters) | - | Raunak | W14 | W15 | 2% | 0% | Not started
WS5.4 | User acceptance testing (UAT) with SVV Balaji - B2B | - | Joint | W15 | W17 | 2% | 0% | Not started
WS5.5 | Backups, monitoring & disaster recovery | - | Ujjawal | W15 | W16 | 1% | 0% | Not started
WS5.6 | Training & handover | - | Joint | W17 | W18 | 1% | 0% | Not started
WS5.7 | Go-live & hypercare - B2B launch | - | Joint | W18 | W18 | 1% | 0% | Not started
WS5.8 | B2C UAT & consumer channel launch [NEW - Decision 1] | - | Joint | W19 | W21 | 1% | 0% | Conditional
| TOTAL WEIGHTED PROJECT COMPLETION |  |  |  |  | 100% | 50.9%
| Weight validation (must equal 100%) |  |  |  |  | OK
Weight % reflects estimated share of total project effort, revised for the added B2C scope.
Yellow rows are B2C activities added by Decision 1 - not in the signed scope of work.

## 3. Weekly Progress
WEEKLY PROGRESS REPORT - WEEK 3, UPDATED 19-AUG-2026
WBS | Activity | Planned % (this wk) | Actual % (this wk) | Variance | Schedule Status | Evidence / Deliverable | Remarks
WS1.1 | Foundation: auth, roles, permissions, CI | 100% | 100% | 0% | On schedule | Swagger API docs; 50 automated tests passing | Complete and verified
WS1.2 | Farm sourcing & farmer traceability | 100% | 100% | 0% | Ahead of schedule | Live demo: farmer approval issues SVV-2026-NNNNNN code + QR/barcode | Complete. Training records confirmed as executive-entered - no farmer app required
WS1.3 | Procurement, batching, warehouse & inventory | 100% | 100% | 0% | Ahead of schedule | Live demo: RM-YYYYMMDD-NNN batch generation; inventory ledger | Complete ahead of plan
WS1.4 | Processing, recipes, QA, packaging | 100% | 100% | 0% | Ahead of schedule | Live demo: full trace from finished pack to farmer | Complete ahead of plan. Multigrain production unblocked and enforcing as of 14-Aug (A-05): blend ratio checked against the approved recipe on every run.
WS1.5 | Sales & order fulfilment (B2B), dispatch & delivery | 5% | 80% | 75% | Ahead of schedule | Order model live end to end: draft, placement with re-pricing, confirmation, batch-wise allocation, pack, dispatch and delivery | A-13 answered 16-Aug and built. Orders now hold a DRAFT state, finished-goods stock moves against the same movement ledger raw material has always used, and a cancelled order keeps its allocation rows marked released rather than deleting them. Dispatch and delivery timestamps added 19-Aug (see A-14) - without them no delivery-performance report is computable, and a timestamp cannot be backfilled. Remaining 20% is invoicing and the e-way bill hand-off, which wait on A-11.
WS1.6 | Channel pricing engine (B2B / B2C) | 0% | 100% | 100% | Ahead of schedule | Live: dated price rules per channel and customer type, quantity breaks, supersede endpoint, resolve endpoint and a B2B/B2C comparison per product | Complete. A rate is never edited in place: superseding closes the current rule and opens a new one, so an invoice raised in June still reproduces June's price years later. Prices are frozen onto the order line at placement, not at draft, so a draft parked for a week cannot lock in a stale rate.
WS1.7 | Consumer (B2C) commerce APIs | 0% | 0% | 0% | Conditional | - | NEW - not in signed SOW. Held pending A-10 cost & timeline agreement
WS2.1 | Admin panel scaffolding, auth, role-based navigation | 0% | 100% | 100% | Ahead of schedule | Live panel: sign-in, session refresh, role-filtered menu across 25 screens | Complete. Also added the missing /auth/refresh, /auth/logout and /auth/me endpoints, without which no client could hold a session beyond 15 minutes.
WS2.2 | Master data, farmer & channel pricing screens | 0% | 100% | 100% | Ahead of schedule | Live screens: branches, users, farmers (registration, approval, QR/barcode), agreements, seed distribution, training, field visits, and multi-plot land profiling per farmer | Complete - the outstanding product and channel-pricing screens landed with WS2.5. Land profiling added 16-Aug: a farmer can hold several plots, each with survey number, soil, irrigation, crop and GPS, and the plot now carries through harvest inspection into the collection and batch, so the consumer trace page resolves to a field rather than only to a farmer.
WS2.3 | Procurement, warehouse & inventory screens | 0% | 100% | 100% | Ahead of schedule | Live screens: procurement plans, harvest inspections, collections, raw material batches with upstream trace, warehouses with per-unit occupancy, batch-wise stock (in/out/transfer/adjust) and the append-only movement ledger | Complete - 6 weeks ahead of baseline. Quality gates surfaced in the UI: only approved farmers can be inspected, only approved inspections collected, and reserved stock cannot be withdrawn. Pending manual test.
WS2.4 | Production, recipe & quality screens | 0% | 100% | 100% | Ahead of schedule | Live screens: products with B2B/B2C pricing, recipes with versioning and approval, cleaning & grading, production batches with per-batch consumption, quality inspections across all three stages, finished goods with QA release, label printing and stock-in | Complete - 8 weeks ahead of baseline. Panel is 22 of 25 screens. Recipe composition rules and quality gates are enforced in the forms, not discovered through server errors. Multigrain production live as of 14-Aug with a blend worksheet showing the required quantity per grain. Pending manual test.
WS2.5 | Sales, dispatch & delivery screens (channel-aware) | 0% | 100% | 100% | Ahead of schedule | Live screens: customers (one registry across both channels, with credit headroom per B2B account), price lists (dated rules, changed by superseding only), orders (draft through delivery, with the allocated batches shown as the picking slip) | Complete - 9 weeks ahead of baseline. The admin panel is now 27 of 27 screens; nothing renders a placeholder. Channel is chosen at customer registration and cannot be changed afterwards, because it decides which price list every future order of theirs resolves against. Allocation is a server action rather than a form: it picks batches first-expiry-first-out from QA-released stock, which the panel could not do correctly on its own.
WS2.6 | Dashboards, reports & analytics screens | 0% | 20% | 20% | Ahead of schedule | Live screen: farm-to-fork trace, now showing plot-level origin. FRD 34 audited line by line 19-Aug | Traceability screen built early for client demonstration. Section 34 names roughly forty reports across nine families; thirty-five are answerable from data already captured. Five are not, and the audit is issued as SVV_Balaji_FRD34_Reporting_Gaps.md - one of the five (delivery timing) was closed immediately rather than raised, because a timestamp is the only kind of data that cannot be reconstructed later. The other three are questions for the client, tracked as A-14. Reporting module build starts once the current build passes.
WS3.1 | Agriculture Expert app (field visits, crop monitoring, training logs) | 0% | 60% | 60% | Ahead of schedule | Installable app at /field with its own login and home-screen icon: today's schedule, farmer onboarding with land profiling, seed distribution, field visits, training sessions and the harvest inspection gate | Built 15-16 Aug as a separate front end rather than a Flutter app - one codebase for validation rules, no app store, installs to the phone home screen from the browser. Camera capture and client-side image compression are in, so a 4 MB field photo uploads as roughly 380 KB over rural mobile data. Remaining 40% is offline capture: a service worker plus a queued write path, which is real work and is the only part of the original brief a website does not get for free.
WS3.5 | Consumer app / website (B2C) | 0% | 0% | 0% | Conditional | - | NEW - not in signed SOW. Held pending A-10
WS4.1 | Cloud object storage | 0% | 80% | 80% | In progress | Live: every photo and document in the system uploads through one interface - farmer KYC, inspection photos, field visit evidence, training materials | No longer blocking. Interim account in use since 14-Aug, with credentials held only in the backend environment file and in no document, chart or repository file. Storage sits behind a single abstract class, so changing provider is one class and one line. A-04 remains open on ownership and permanence, not capability.
WS4.4 | GST e-invoicing & e-way bill via GSP | 0% | 0% | 0% | On schedule | - | UNBLOCKED 11-Aug by Decision 2. Awaiting GSP vendor + credentials (A-11)
WS4.5 | Payment gateway (Razorpay) | 0% | 0% | 0% | Conditional | - | Moved from On hold to in scope - B2C requires online collection
WS5.1 | Automated test suite & CI | 45% | 45% | 0% | Ahead of schedule | 50 unit tests + 90 integration checks, all passing | Ongoing throughout project
| OVERALL PROJECT COMPLETION (weighted) |  | 50.9%
Frontend is complete against the current scope and running well ahead of baseline. The admin panel is 27 of 27 screens - WS2.1 through WS2.5 all complete, between 4 and 9 weeks earlier than the proposed schedule - and the Agriculture Expert app is live as an installable field app. Role-based access was rebuilt on 16-Aug so a Super Admin can grant any page to any role from the panel without a redeploy; on a project where who does what will keep changing, that was a release cycle per administrative decision. Only WS2.6 (dashboards and reports) remains open in the panel workstream.
No activity is DELAYED. A-13 CLOSED 16-Aug and is built. A-14 raised 19-Aug covering three reporting inputs FRD 34 assumes and the system does not capture - production cost, machine utilisation and the credit-period start date; the fourth gap, delivery timing, was closed the same day rather than raised. A-12 (pagination and response envelope) is now 6 days past its target with no pagination DTO in the backend: all 27 panel screens absorb it through an adapter so nothing is blocked, but the movement ledger, production and quality lists grow monotonically and will be the first to become unusable on production data. A-04 remains open on storage ownership. A-10 and A-11 both passed their 18-Aug target and are now overdue.

## 4. Action Tracker
CONSOLIDATED ACTION TRACKER
Open actions remain on this tracker until formally closed. Ageing is calculated automatically from the date raised. A-02 and A-03 closed 11-Aug-2026; A-05 closed 14-Aug; A-13 closed 16-Aug. A-14 raised 19-Aug-2026.
Ref | Action Item | Raised On | Responsible | Target Date | Status | Ageing (days) | Priority | Closure Remarks
A-01 | Approve the revised activity-wise schedule baseline (Sheet 2) so future reporting has an agreed reference | 2026-08-07 | SVV Balaji | 2026-08-14 | Open | 12 | Critical | Baseline revised 11-Aug for the added B2C scope - please review the revision
A-02 | Decision 1: confirm sales channel scope - B2B only, or consumer/marketplace channels also | 2026-08-07 | SVV Balaji | 2026-08-12 | Closed |  | Critical | CLOSED 11-Aug-2026. Both B2B and B2C confirmed, with separate pricing per channel. Scope impact raised as A-10
A-03 | Decision 2: confirm GST e-invoicing applicability and preferred provider | 2026-08-07 | SVV Balaji - Finance | 2026-08-14 | Closed |  | Critical | CLOSED 11-Aug-2026. GST Suvidha Provider route approved. Vendor and credentials now tracked as A-11
A-04 | Decision 3: approve cloud object storage provider and confirm whether QR process videos are required | 2026-08-07 | SVV Balaji | 2026-08-21 | Open | 12 | Critical | Escalation note issued 14-Aug (SVV_Balaji_A04_Storage_Decision_Note.md), target moved to 21-Aug. NO LONGER BLOCKING: an interim Cloudinary account is in use from 14-Aug, so the field executive module and all photo capture ship on schedule. Storage sits behind a single interface in the codebase, so switching provider later is one class and one line. The open question is now ownership and permanence rather than capability - the account must be opened in SVV Balaji's name so media and billing belong to the client. Also needs a retention and access policy for farmer KYC images (Aadhaar, PAN), which shapes access control not just storage.
A-05 | Decision 4: confirm multigrain (blended) production is in scope | 2026-08-07 | SVV Balaji | 2026-08-14 | Closed |  | High | CLOSED 14-Aug-2026. Multigrain (blended) production confirmed in scope. The MULTIGRAIN_ENABLED flag has been removed rather than switched on, so a stale .env cannot silently re-block it. Blend ratio is now enforced at production time: a run whose mix drifts more than 0.5 percentage points from the approved recipe, or omits one of its grains, is refused. The admin panel shows the required quantity per grain and a live share as the operator selects batches.
A-06 | Provide existing customer and product master data for migration planning | 2026-08-07 | SVV Balaji | 2026-08-28 | Open | 12 | Medium | Now also needs consumer-facing product descriptions and images for the B2C catalogue
A-07 | Nominate SVV Balaji UAT participants and confirm availability window | 2026-08-07 | SVV Balaji | 2026-08-28 | Open | 12 | Medium
A-08 | Confirm hosting upgrade path - current single VPS insufficient for media storage at scale | 2026-08-07 | Joint | 2026-08-21 | Open | 12 | High | More urgent under B2C - consumer QR traffic hits public endpoints
A-09 | Set up staging environment for SVV Balaji review access | 2026-08-07 | Appzeto | 2026-08-21 | Open | 12 | Medium
A-10 | Agree cost and timeline for the added B2C scope in writing, before the consumer workstream starts | 2026-08-11 | Ravi Tiwari / SVV Balaji | 2026-08-18 | Open | 8 | Critical | Consumer app, accounts, cart, payments and B2C invoicing are outside the signed SOW. B2B build continues meanwhile
A-11 | Confirm GSP vendor (ClearTax recommended), company GSTIN and sandbox/production API credentials | 2026-08-11 | SVV Balaji - Finance | 2026-08-18 | Open | 8 | Critical | Provider onboarding is an external process - needed early to leave runway before dispatch go-live
A-12 | Agree pagination and response envelope for all list endpoints - proposal issued (SVV_Balaji_A12_Pagination_and_Envelope_Proposal.md) | 2026-08-11 | Ujjawal / Raunak | 2026-08-13 | Open | 8 | High | Internal. Target date reached 13-Aug with no pagination DTO in the backend, now 6 days overdue. All 27 admin panel screens are built against the unpaginated shape - an adapter absorbs the change, so this is still a non-breaking fix rather than a rework - but the movement ledger, production and quality lists all grow monotonically and will be the first to become unusable on production data. Written proposal issued 11-Aug.
A-13 | Decide: order DRAFT state, finished-goods stock movement ledger, and allocation history retention on cancellation | 2026-08-11 | Ujjawal / Raunak | 2026-08-15 | Closed |  | Medium | CLOSED 16-Aug-2026, all three answered yes and built. Orders now open in DRAFT, with the price resolved and frozen onto the line at placement rather than at draft - a draft parked for a week is placed at that week's rate, and any line that moved is shown back before the order commits. Finished-goods stock now writes to the same StockMovement ledger raw material has always used, rather than a second table. Cancelling an order marks its allocations released with a reason instead of deleting them, so "you reserved me that batch and then cancelled" has an answer in the data.
A-14 | Confirm three reporting inputs FRD 34 assumes: per-batch production cost, what "machine utilisation" should measure, and the date a credit period runs from (SVV_Balaji_FRD34_Reporting_Gaps.md) | 2026-08-19 | SVV Balaji / Ujjawal | 2026-08-26 | Open | 0 | High | FRD 34 names ~40 reports; 35 are answerable from data already captured. Five are not. Delivery timing was the fifth and has been closed unilaterally - dispatch and delivery timestamps were added 19-Aug, because a timestamp cannot be backfilled and every order shipped before the fix would have been permanently unmeasurable. The three remaining need a client answer: (1) production cost - nothing records what it costs to convert raw material, so Profit Analysis can only show gross margin over raw material; recommend one figure per batch at completion. (2) Machine utilisation - machine is free text with no run times, so no percentage is computable; recommend a machine master and run counts. (3) Credit period - CREDIT_30 has never been defined as 30 days from what, so "overdue" is not currently computable; recommend dispatch date. If unanswered, WS2.6 ships the 35 reports that have inputs and the rest name the missing field rather than showing an empty chart.
| Open actions: | 10
| Critical priority open: | 4
| Closed this week: | 4
Formulas:
Ageing (days) = IF([Status]="Closed","",TODAY()-[Raised On])